## it should be a comprehensive 15
Week | Task | Activity | Duration (Days) | Deliverables | Resources
Week 1 | Develop RFP & Selection Criteria (A.1) | Conduct Stakeholder Interviews to Define Project Goals & Scope | 2 | Project Goals & Scope Document | Project Team (Lead, Members), Stakeholders
|  | Research Industry Best Practices for Import/Export Automation | 1 | Compiled Industry Best Practices Report | Project Team (Research Specialist), Online Resources
|  | Develop Skills & Experience Matrix for Required Consultant Expertise | 1 | Skills & Experience Matrix Document | Project Team (Lead), Industry Experts
|  | Draft Evaluation Criteria Aligned with Project Needs & Consultant Expertise | 2 | Evaluation Criteria Document | Project Team (Lead), Stakeholders
|  | Collaborate with Procurement Specialist to Draft Initial RFP Document | 1 | Draft RFP Document | Project Team (Lead, Procurement Specialist)
Week 2 | A.1 Refine RFP & Obtain Approvals | 1. Refine RFP Document based on Stakeholder Feedback | 1 | - Revised Draft RFP Document | - Project Team (Lead), Stakeholders
|  | 2. Secure Internal Approvals (Project Management & Procurement) on Final RFP | 1 | - Approved RFP Document | - Project Team (Lead), Procurement Specialist
A.2 Shortlist Potential Consulting Firms
|  | 3. Identify Potential IT Consulting Firms through Targeted Online Platforms & Industry Networks | 2 | - Shortlisted Consulting Firms List | - Project Team (Procurement Specialist)
|  | 4. (Optional) Develop & Distribute Pre-qualification Questionnaire | 1 (Optional) | - Pre-qualification Responses from Firms (Optional) | - Project Team (Procurement Specialist)
Week 3 | Shortlist and Evaluate IT Consulting Firms (A.2) | 1. Evaluate Proposals based on Defined Criteria (Review Team Meetings) | 3 | - Shortlisted Proposals with Evaluation Scores | - Evaluation Team (Project Team Members, Subject Matter Experts)
|  | 2. Conduct Presentations & Q&A Sessions with Shortlisted Firms (Focus on Technical Approach) | 2 | - Presentation Recordings & Meeting Minutes | - Evaluation Team, Shortlisted Firms
|  | 3. (Optional) Analyze Pre-qualification Responses (if applicable) | 1 (Optional) | - Shortlisted Firms Based on Pre-qualification (Optional) | - Evaluation Team (Optional)
Week 4 | Finalize Shortlist and Negotiate Contract (A.2) | 1. Finalize Shortlist of Consulting Firms Based on Evaluation & Presentations | 1 | - Shortlisted Consulting Firms List | - Evaluation Team
|  | 2. Conduct Reference Checks on Top Candidates | 1 | - Reference Check Reports | - Project Team (Procurement Specialist)
Week 5 | Onboard Consulting Firm and Develop Project Management Plan (A.3) | 1. Organize Collaborative Onboarding Workshop (Project Goals, Communication, Risk Management) | 2 | - Workshop Agenda & Action Items | - Project Team, Consulting Firm Team
|  | 2. Facilitate Knowledge Transfer Sessions on Import Process, Existing Systems & Stakeholders | 2 | - Knowledge Transfer Session Materials | - Project Team Subject Matter Experts, Consulting Firm Team
Week 6 | Finalize Project Management Plan & Initiate Field Visit Planning (A.3 & B.1) | Refine & Finalize Project Management Plan with Consulting Firm Input | 1 | - Finalized Project Management Plan Document | - Project Team, Consulting Firm Team
Week 7 | Finalize Field Visit Preparations & Conduct Initial Data Collection (B.1 & B.2) | 1. Secure Necessary Permits and Access for Port Visit | 1 | - Obtained Permits & Access Confirmations | - Project Team (Logistics Specialist)
|  | 2. Refine Field Visit Plan with Stakeholder Engagement Strategy | 1 | - Finalized Field Visit Plan Document | - Project Team (Communication Specialist)
|  | 3. Prepare Data Collection Tools (Questionnaires, Interview Guides) | 1 | - Data Collection Tools (Finalized) | - Project Team (Research Specialist)
Week 8 | Continue Field Visit Data Collection & Analysis (B.2 & B.3) | 1. Conduct Interviews with Key Stakeholders (Gather Insights & Challenges) | 2 | - Transcribed Interviews & Key Findings Summary | - Field Visit Team (Interview Specialist)
|  | 2. Continue Shadowing Licensed Customs Agents through Clearing Process | 1 | - Additional Field Observation Notes & Photos | - Field Visit Team
|  | 3. Observe and Document Existing Import/Export Processes (Data Flow, Workflows) | 2 | - Process Flow Diagrams & Documentation (Initial) | - Field Visit Team (Process Mapping Specialist)
Week 9 | Continued Field Visit Data Collection & Analysis (B.2 & B.3) | 1. (Optional) Conduct Additional Stakeholder Interviews | 1 (Optional) | - Transcribed Interviews & Key Findings Summary (Additional) | - Field Visit Team (Interview Specialist)
|  | 2. Finalize Shadowing of Licensed Customs Agents | 1 | - Consolidated Field Observation Notes & Photos | - Field Visit Team
|  | 3. Refine & Finalize Process Flow Diagrams & Documentation | 1 | - Finalized Process Flow Diagrams & Documentation | - Field Visit Team (Process Mapping Specialist)
Week 10 | Streamline Import/Export Processes (B.3) | Data Bottleneck Analysis | 2 | Collaborate with IT consultant to analyze import/export data (delays, errors, approvals). Identify recurring bottlenecks causing inefficiencies and cost increases. Use data visualization to present findings. | Data Analysis Report with Bottleneck Identification
|  | Consolidate Stakeholder & Field Visit Findings | 2 | Analyze qualitative data (interviews, observations, process flows). Identify common themes and challenges from stakeholders. Combine data and field visit findings into a report. | Consolidated Findings Report
|  | Brainstorm Initial Recommendations | 1 | Based on combined findings, brainstorm initial recommendations for process improvement and automation. Consider solutions that address bottlenecks, improve efficiency, and enhance data accuracy. Collaborate with IT consultant on potential automation solutions. | Initial Recommendations Report (may be merged with Consolidated Findings Report)
|  | Prioritize Recommendations | 1 | Evaluate and prioritize initial recommendations based on impact and feasibility. Consider impact on efficiency, cost reduction, and user experience. Assess technical complexity, resource requirements, and integration challenges. Develop a prioritized list focusing on high-impact, feasible solutions aligned with project goals and budget. | Prioritized Recommendations List
|  | Finalize Recommendations Report | 1 | Refine and document prioritized recommendations in a report. Outline the rationale, potential benefits, and estimated impact for each recommendation. | Consolidated Findings Report (may include Initial Recommendations)
Week 11 | Refine Scope & Assess Feasibility (B.3 & C.1) | Refine Recommendations & Define Scope | 2 | - Conduct workshop with stakeholders (optional) to gather feedback on prioritized recommendations. - Collaborate with IT consultant to refine recommendations based on stakeholder input and technical feasibility. - Develop Automation Scope Document outlining specific processes and functionalities targeted for automation. | - Refined Prioritized Recommendations List - Automation Scope Document
|  | System Architecture | 1 | - Work with IT consultant to create a High-Level System Architecture Diagram. - The diagram should visually represent the proposed technical solution (existing systems, new automation tools, data flow, interactions). | - High-Level System Architecture Diagram
|  | Feasibility Analysis | 2 | - Conduct a comprehensive Feasibility Study with the IT consultant, covering: Technical Feasibility: Assess technology integration and project requirement fulfillment. Economic Feasibility: Analyze costs (investment, maintenance) and potential ROI (efficiency gains, cost reduction). Operational Feasibility: Evaluate impact on workflows, user adoption, and training needs. | - Feasibility Study Report
Week 12 | Plan & Secure Funding (C.1 & C.2) | Develop Detailed Project Plan | 2 | - Translate findings (scope, architecture, feasibility) into a detailed project plan. - Define phases, timelines (milestones), resource allocation (personnel, budget), communication plan, risk management & change management strategies. - Utilize project management software (optional) for visualization and progress tracking. | - Detailed Project Plan
|  | Cost Estimate & Resource Breakdown | 1 | - Collaborate with IT consultant to develop a detailed cost estimate (hardware, software, implementation, maintenance, training). - Break down resource allocation (internal teams, IT consultant) by personnel hours. | - Cost Estimate & Resource Breakdown Document
|  | Project Proposal & Budget Justification | 1 | - Develop a comprehensive project proposal outlining goals, scope, automation solutions, system architecture, and expected benefits (based on feasibility study). - Clearly justify budget allocation by highlighting potential cost savings, efficiency gains, and improved operational performance. - Consider including key findings and recommendations from the stakeholder workshop (if conducted in Week 11). | - Project Proposal & Budget Justification Document
|  | Present & Secure Budget Approval | 1 | - Prepare a clear and concise presentation for stakeholders (sponsors, executives). - Present proposal, cost estimate, budget justification, address concerns, and clarify questions. - Secure formal budget approval from stakeholders for project execution. | - Stakeholder Presentation Materials
Week 13 | Refine Project & Initiate Procurement (C.3 & D.1) | Develop Procurement Strategy | 1 | Define the overall vendor selection and contract negotiation approach. Consider factors like: Bidding process (open vs. invitation-only) Evaluation criteria weighting (importance of different factors) Vendor selection timeline | Procurement Strategy Document
|  | Develop RFP Document | 2 | Collaborate with the IT consultant to draft a comprehensive RFP document. Include: Project background and goals Scope of automation requirements and desired functionalities Defined vendor selection criteria from Week 14 Instructions for proposal submission, response timeline, and contact information for clarification questions | Request for Proposal (RFP) Document
|  | Issue RFP to Shortlisted Vendors | 1 | Distribute the finalized RFP document to all shortlisted vendors identified in Week 14. Ensure clear communication regarding the proposal submission deadline and any additional instructions. | RFP Distribution Records
Week 14 | Evaluate Proposals & Select Vendor (D.2 & D.3) | Evaluate Vendor Proposals (2) | - Review and evaluate proposals submitted by shortlisted vendors against the defined selection criteria established in Week 13 (RFP document). - Assess each proposal's: Technical capabilities Functionality alignment with project requirements Implementation methodology Security features Scalability Compatibility with existing systems - Evaluate proposed costs (licensing, implementation, ongoing maintenance) and consider the total cost of ownership (TCO) over the project lifecycle. | - Vendor Proposal Evaluation Matrix
|  | Conduct Vendor Presentations (1) | - Shortlist a final few vendors based on the initial proposal evaluation. - Invite shortlisted vendors to present their proposed solutions in detail, addressing any questions or clarifications from the project team. - Use presentations as an opportunity to assess vendor experience, communication style, and understanding of the project goals. | - Presentation Evaluation Notes
|  | Select Preferred Vendor (1) | - Based on the combined evaluation of proposals and presentations, select the preferred vendor who best demonstrates the ability to meet project requirements, deliver value, and ensure a successful automation implementation. | - Vendor Selection Decision Document
|  | Initiate Contract Negotiation (Optional) (1) | - Begin preliminary contract negotiations with the selected vendor, outlining key terms and conditions such as pricing, project timelines, deliverables, warranties, and service level agreements (SLAs). | - Draft Contract Terms (Optional)
Week 15 | Contract Negotiation & Project Kick-off (D.3 & C.3)
|  | Contract Negotiation & Finalization (2) |  | - Conduct detailed contract negotiations with the selected vendor to finalize key terms and conditions such as: Pricing structure (licensing, implementation, ongoing maintenance) Project timelines and milestones Deliverables and acceptance criteria Warranties and guarantees Service level agreements (SLAs) - Ensure the contract aligns with project goals, budget, and risk management strategies. | - Finalized Contract with Selected Vendor
|  | Project Kick-off Meeting (1) |  | - Conduct a formal project kick-off meeting with representatives from the selected vendor, internal project team members, and key stakeholders. - Review the finalized project plan, timelines, roles & responsibilities, communication plan, and risk management strategies. - Address any initial questions or concerns from stakeholders and establish a collaborative working environment for project execution. | - Project Kick-off Meeting Minutes & Action Items